## Project Overview
AGILE PROJECT DOCUMENT
E-Commerce Product Recommendation System
Prepared for Academic Submission ¦ Version 1.0 ¦ April 2025
PROJECT INFORMATION
Project Name | E-Commerce Product Recommendation System | Project Code | ECRS-2025
Department | Computer Science & Engineering | Semester | 3rd Year / Semester VI
Project Type | Machine Learning / Web Application | Methodology | Agile (Scrum)
Start Date | 03-February-2025 | End Date | 2025-04-02
Team Size | 1 (Individual Project) | Supervisor | Simran
Student Name | Pavithra N | Register No.
PROJECT DESCRIPTION
This project develops an intelligent E-Commerce Product Recommendation System using collaborative filtering and content-based filtering techniques. The system analyzes user purchase history, browsing behavior, and product attributes to deliver personalized product suggestions, improving customer experience and increasing sales conversion. Built using Python (scikit-learn, pandas), Flask REST API, and a React frontend, the system follows an Agile Scrum methodology with 4 sprints over 8 weeks.
TECHNOLOGY STACK
Layer | Technology | Purpose | Version
Data Processing | Python / Pandas / NumPy | Data cleaning, preprocessing, matrix operations | Python 3.10+
ML Algorithms | Scikit-learn / Surprise | Collaborative & Content-based filtering | 1.3+
Backend API | Flask / Flask-RESTful | REST API for recommendation serving | 2.3+
Frontend | React.js / Axios | UI for product display & recommendations | 18+
Database | MySQL / SQLAlchemy | User, product, and interaction data storage | 8.0+
Version Control | Git / GitHub | Source code management | Latest

## Product Backlog
PRODUCT BACKLOG — E-Commerce Recommendation System
Prioritized list of all features and requirements ¦ MoSCoW Priority ¦ Story Points
# | User Story ID | As a... | I want to... | So that... | Priority | Story Points | Sprint | Status | Acceptance Criteria
1 | US-001 | Data Scientist | collect and load user purchase & product datasets | I can build the recommendation model | Must Have | 5 | Sprint 1 | Done | Datasets loaded with >10K records; schema validated
2 | US-002 | Data Scientist | clean and preprocess raw data (nulls, duplicates, normalize) | data quality is ensured for accurate model training | Must Have | 5 | Sprint 1 | Done | Zero null values; duplicate rows removed; data normalized
3 | US-003 | Data Scientist | perform EDA on user behavior and product data | I understand patterns and guide model design | Must Have | 3 | Sprint 1 | Done | EDA report with 5+ charts; key patterns documented
4 | US-004 | Data Scientist | build a user-item interaction matrix | collaborative filtering can compute similarities | Must Have | 5 | Sprint 1 | Done | Matrix built; cosine similarity computed successfully
5 | US-005 | Developer | implement collaborative filtering (user-based & item-based) | users get recommendations based on similar users' behavior | Must Have | 8 | Sprint 2 | Done | Precision@10 > 0.75; handles cold-start fallback
6 | US-006 | Developer | implement content-based filtering using product attributes | users see recommendations based on product similarity | Must Have | 8 | Sprint 2 | Done | TF-IDF / cosine similarity used; results relevant
7 | US-007 | Developer | build a hybrid recommendation model | recommendation accuracy is maximized | Should Have | 8 | Sprint 2 | Done | Hybrid score > individual models; weight tunable
8 | US-008 | Developer | evaluate model using RMSE, Precision@K, Recall@K | model quality is measured objectively | Must Have | 3 | Sprint 2 | Done | RMSE < 1.0; Precision@10 > 0.75; Recall@10 > 0.70
9 | US-009 | Developer | build Flask REST API endpoint for recommendations | the frontend can fetch personalized product suggestions | Must Have | 5 | Sprint 3 | Done | GET /recommend/{user_id} returns top-10 products in JSON
10 | US-010 | Developer | implement caching for recommendation API | response time is reduced for repeated requests | Should Have | 3 | Sprint 3 | Done | API response < 2 seconds; cache hit rate > 80%
11 | US-011 | End User | see personalized product recommendations on the homepage | I discover products relevant to my interests | Must Have | 5 | Sprint 3 | Done | Top 10 products displayed; no duplicates; relevant
12 | US-012 | End User | see 'Similar Products' on a product detail page | I can explore related items easily | Should Have | 5 | Sprint 3 | Done | 5 similar products shown based on attributes
13 | US-013 | End User | receive email recommendations weekly | I am reminded of products I might like | Could Have | 3 | Sprint 4 | Pending | Email sends successfully with 5 product suggestions
14 | US-014 | Admin | view a dashboard showing recommendation accuracy metrics | I can monitor system health and performance | Should Have | 5 | Sprint 4 | Done | Dashboard shows RMSE, CTR, coverage; auto-refreshes
15 | US-015 | Developer | write unit tests for all modules | code quality and reliability is ensured | Must Have | 5 | Sprint 4 | Done | 100% of core functions tested; all tests pass
16 | US-016 | Developer | deploy the system to a production-like environment | the application is accessible for demonstration | Must Have | 5 | Sprint 4 | Done | App live on local/Heroku; no critical errors on startup
TOTAL STORY POINTS |  |  |  |  | 81

## Sprint Plan
SPRINT PLAN — E-Commerce Recommendation System
SPRINT 1: Data Collection, Cleaning & EDA
Sprint Duration: |  | 03 Feb 2025 – 14 Feb 2025 |  | 🎯 Sprint Goal: Prepare clean, analysis-ready datasets and understand user behavior patterns through EDA
# | Story ID | Task Description | Assigned To | Est. Duration | Story Pts | Status
1 | US-001 | Collect datasets: Amazon product data + user interaction logs | Data Scientist | 3 days | 5 | Done
2 | US-002 | Data cleaning: handle nulls, remove duplicates, normalize features | Data Scientist | 3 days | 5 | Done
3 | US-003 | Exploratory Data Analysis: user behavior, product popularity, rating distribution | Data Scientist | 3 days | 3 | Done
4 | US-004 | Build user-item interaction matrix & compute cosine similarity | Data Scientist | 3 days | 5 | Done
Sprint 1 Total Story Points |  |  |  |  | 18
SPRINT 2: Algorithm Development & Model Evaluation
Sprint Duration: |  | 17 Feb 2025 – 28 Feb 2025 |  | 🎯 Sprint Goal: Implement and evaluate collaborative filtering, content-based, and hybrid recommendation algorithms
# | Story ID | Task Description | Assigned To | Est. Duration | Story Pts | Status
1 | US-005 | Implement user-based & item-based collaborative filtering | Developer | 4 days | 8 | Done
2 | US-006 | Implement content-based filtering using TF-IDF on product descriptions | Developer | 3 days | 8 | Done
3 | US-007 | Build weighted hybrid model combining both approaches | Developer | 3 days | 8 | Done
4 | US-008 | Evaluate model: RMSE, Precision@10, Recall@10, F1-Score | Developer | 2 days | 3 | Done
Sprint 2 Total Story Points |  |  |  |  | 27
SPRINT 3: Backend API & Frontend Integration
Sprint Duration: |  | 03 Mar 2025 – 14 Mar 2025 |  | 🎯 Sprint Goal: Expose recommendations via REST API and integrate with React frontend for end-to-end user experience
# | Story ID | Task Description | Assigned To | Est. Duration | Story Pts | Status
1 | US-009 | Build Flask REST API: /recommend/{user_id} endpoint | Developer | 3 days | 5 | Done
2 | US-010 | Add Redis/in-memory caching to API for <2s response time | Developer | 2 days | 3 | Done
3 | US-011 | Build React homepage component showing top-10 recommendations | Frontend Dev | 4 days | 5 | Done
4 | US-012 | Add 'Similar Products' section on product detail page | Frontend Dev | 3 days | 5 | Done
Sprint 3 Total Story Points |  |  |  |  | 18
SPRINT 4: Testing, Dashboard & Deployment
Sprint Duration: |  | 17 Mar 2025 – 30 Apr 2025 |  | 🎯 Sprint Goal: Ensure quality through testing, monitor performance via admin dashboard, and deploy the system
# | Story ID | Task Description | Assigned To | Est. Duration | Story Pts | Status
1 | US-013 | Implement weekly email recommendation feature (optional) | Developer | 2 days | 3 | Pending
2 | US-014 | Build admin analytics dashboard: RMSE, CTR, coverage metrics | Developer | 4 days | 5 | Done
3 | US-015 | Write unit tests for all modules (data, model, API, frontend) | Developer | 4 days | 5 | Done
4 | US-016 | Deploy to local server / Heroku; write user and technical documentation | Developer | 4 days | 5 | Done
Sprint 4 Total Story Points |  |  |  |  | 18

## Defect Tracker
DEFECT TRACKER — E-Commerce Recommendation System
Log of all defects identified, resolved, and verified during development
Sl No | Defect ID | Submitted By | Submitted Date | Description | Sprint | Type | Action Taken | Action Date | Status | Remarks
1 | DEF-001 | [Your Name] | 05 Feb 2025 | Missing values in user purchase history causing NaN errors in user-item matrix | Sprint 1 (Weeks 1–2) | Logical | Cleaned dataset using pandas fillna() and dropna(); validated schema | 05 Feb 2025 | Closed | User-item matrix built successfully
2 | DEF-002 | [Your Name] | 10 Feb 2025 | KeyError when product ID not found in product feature dictionary | Sprint 1 (Weeks 1–2) | Logical | Added .get() with default value and try-except error handling | 10 Feb 2025 | Closed | No KeyError on missing products
3 | DEF-003 | [Your Name] | 17 Feb 2025 | Collaborative filtering gives irrelevant results for new/cold-start users | Sprint 2 (Weeks 3–4) | Logical | Implemented popularity-based fallback for users with <3 interactions | 17 Feb 2025 | Closed | New users get top-10 popular products
4 | DEF-004 | [Your Name] | 21 Feb 2025 | Content-based model recommends duplicate products for the same query | Sprint 2 (Weeks 3–4) | Maintainability | Added de-duplication filter using set() before returning results | 21 Feb 2025 | Closed | Recommendations are unique
5 | DEF-005 | [Your Name] | 03 Mar 2025 | API response time exceeds 5 seconds for large user bases | Sprint 3 (Weeks 5–6) | Standards | Implemented in-memory LRU caching; optimized similarity matrix lookup | 03 Mar 2025 | Closed | Response time < 2 seconds
6 | DEF-006 | [Your Name] | 10 Mar 2025 | CORS error blocking frontend React app from calling Flask API | Sprint 3 (Weeks 5–6) | Logical | Added Flask-CORS extension with proper origin configuration | 10 Mar 2025 | Closed | Frontend-API integration working
7 | DEF-007 | [Your Name] | 14 Mar 2025 | Frontend renders wrong product images (URL mismatch in API response) | Sprint 3 (Weeks 5–6) | User Interface | Fixed image URL field mapping in API serializer and React component | 14 Mar 2025 | Closed | Product images display correctly
8 | DEF-008 | [Your Name] | 24 Mar 2025 | Unit test fails for edge case: user with no purchase history | Sprint 4 (Weeks 7–8) | Logical | Updated recommendation function to handle empty interaction history | 24 Mar 2025 | Closed | All unit tests pass
9 | DEF-009 | [Your Name] | 31 Mar 2025 | Admin dashboard metrics not refreshing on data update | Sprint 4 (Weeks 7–8) | User Interface | Added auto-refresh interval (30s) and reactive state management | 31 Mar 2025 | Closed | Dashboard updates automatically
10 | DEF-010 | [Your Name] | 07 Apr 2025 | Deployment fails due to missing environment variables on server | Sprint 4 (Weeks 7–8) | Standards | Documented all required env vars; created .env.example file | 07 Apr 2025 | Closed | Application deploys successfully
DEFECT SUMMARY | [8 empty] | 10 | Defects Closed

## Unit Test Plan
UNIT TEST PLAN — E-Commerce Recommendation System
Comprehensive test cases for all system modules ¦ Sprint-wise organization
Sl No | Test Case Name | Test Procedure | Condition to be Tested | Expected Result | Actual Result | Status
1 | Data Loading | Load CSV datasets into pandas DataFrames | Files exist at correct path; format is CSV | DataFrames created with correct columns and row count | Data loaded successfully; shape validated | Pass
2 | Missing Value Handling | Call clean_data() on dataset with null values | Dataset has 10% missing values in rating column | All nulls filled with mean; no NaN in output DataFrame | Nulls filled correctly; DataFrame validated | Pass
3 | Duplicate Removal | Call remove_duplicates() on dataset | Dataset has 50 duplicate user-product rows | All duplicate rows removed; unique records only | 52 duplicates removed; dataset clean | Pass
4 | User-Item Matrix Build | Call build_matrix(df) with cleaned interaction data | User and product IDs available; ratings present | Sparse matrix of shape (users × products) created | Matrix built; shape (9800×1500) confirmed | Pass
5 | Collaborative Filtering – Known User | Call get_cf_recommendations(user_id=101, k=10) | User 101 exists; has 15 purchase interactions | List of 10 unique product IDs returned | Returned [PID223, PID445, ...] — 10 unique items | Pass
6 | Collaborative Filtering – Cold-Start User | Call get_cf_recommendations(user_id=9999, k=10) | User 9999 has zero interactions | Fallback: top-10 most popular products returned | Returned popularity-ranked top-10 list | Pass
7 | Content-Based Filtering | Call get_cb_recommendations(product_id='B001', k=5) | Product B001 exists; TF-IDF matrix built | 5 similar products returned based on cosine similarity | Returned 5 products from same/similar category | Pass
8 | Hybrid Model Score | Call hybrid_recommend(user_id=101, k=10) | Both CF and CB models initialized; weights set (0.6, 0.4) | Top 10 products with combined hybrid scores returned | Hybrid scores computed; 10 products returned | Pass
9 | RMSE Evaluation | Call evaluate_model(test_set) on held-out data | 20% test split; ground truth ratings available | RMSE value < 1.0 on test dataset | RMSE = 0.87 (within acceptable range) | Pass
10 | Precision@10 Metric | Call precision_at_k(recommendations, ground_truth, k=10) | Ground truth relevant items list available | Precision@10 >= 0.75 | Precision@10 = 0.78 | Pass
11 | Flask API – Valid User | GET /recommend/101 | User 101 in database; model loaded | HTTP 200; JSON with 'user_id' and 'recommendations' list | 200 OK; 10 recommendations returned | Pass
12 | Flask API – Invalid User | GET /recommend/99999 | User 99999 does not exist | HTTP 404; JSON error message returned | 404 Not Found; {error: 'User not found'} | Pass
13 | API Response Time | Measure time for GET /recommend/101 with caching | Cache populated; model pre-loaded | Response time < 2000ms | Average response: 480ms | Pass
14 | Duplicate Filter in Output | Call filter_duplicates(product_list) | List contains 3 duplicate product IDs | Output list has no duplicates | Duplicates removed; unique list returned | Pass
15 | Frontend Recommendation Render | Load homepage; verify recommendation cards render | API returns 10 products; React state initialized | 10 product cards displayed with image, name, price | All 10 cards rendered correctly | Pass
16 | Email Recommendation Feature | Trigger send_recommendation_email(user_id=101) | User email in database; SMTP configured | Email sent with 5 product recommendations | Email queued; delivery confirmed in logs | Pending
17 | Admin Dashboard Metrics | Load /admin/dashboard in browser | System has processed >100 recommendations | RMSE, CTR, coverage metrics shown; auto-refresh active | Dashboard loads with correct metrics | Pass
18 | End-to-End System Test | Register user → browse → get recommendations | Full system deployed; all modules connected | Relevant recommendations shown within 2 seconds | System works end-to-end; response in 1.2s | Pass
TEST EXECUTION SUMMARY |  |  |  |  | 17 Pass ¦ 1 Pending ¦ 0 Fail

## Burndown Chart
SPRINT BURNDOWN CHART DATA — E-Commerce Recommendation System
Tracks remaining story points vs ideal burndown across all 4 sprints
Week | Sprint | Ideal Remaining Points | Actual Remaining Points | Completed This Week | Cumulative Done
0 | Project Start | 72 | 72 | 0 | 0
1 | Sprint 1 – Week 1 | 63 | 54 | 18 | 18
2 | Sprint 1 – Week 2 | 54 | 36 | 18 | 36
3 | Sprint 2 – Week 3 | 45 | 19 | 17 | 53
4 | Sprint 2 – Week 4 | 36 | 5 | 14 | 67
5 | Sprint 3 – Week 5 | 27 | 3 | 10 | 77
6 | Sprint 3 – Week 6 | 18 | 0 | 8 | 85
7 | Sprint 4 – Week 7 | 9 | 8 | 5 | 90
8 | Sprint 4 – Week 8 | 0 | 3 | 5 | 95